## README
AI Talent Manager — Engineering Tracker
Purpose | Module-wise implementation tracker for the locked planning baseline.
Daily run | Default 10:00 local time; configurable; Manual Run Now uses the same orchestrator.
Execution modes | APPLICATION / RECRUITER DM / LINKEDIN POST each independently MANUAL or AUTONOMOUS; initial default MANUAL.
Approval | Email approve/reject preferred; dashboard fallback; same execution request abstraction.
Queue loop | Inspect queue → process queue → discover only if needed → match → tailor → execute → save outcome → repeat → preserve leftovers.
Security | Security is P0 and must be enforced before autonomous execution.
Status values | Not Started / In Progress / Blocked / Review / Done
Priority values | P0 / P1 / P2
Test values | Not Started / Passing / Failing / N/A
Checkbox-like fields | Use dropdowns ☐ No / ☑ Yes for Blocked? and Security Review?

## Master Tracker
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
FOUND-001 | Foundation & Config | Project configuration | Define runtime config schema and environment loading | P0 | Not Started |  | 4 |  |  |  | Not Started | Validated config loads with safe defaults. |  | ☐ No | ☐ No
FOUND-001 | Foundation & Config | Project configuration | Add daily run time/timezone/default 10:00 and daily application target | P0 | Not Started | FOUND-001 | 3 |  |  |  | Not Started | Defaults are 10:00 and configurable; invalid values fail closed. |  | ☐ No | ☐ No
FOUND-001 | Foundation & Config | Project configuration | Add independent application/DM/post execution mode variables, default MANUAL | P0 | Not Started | FOUND-001 | 3 |  |  |  | Not Started | Each mode accepts MANUAL/AUTONOMOUS and defaults to MANUAL. |  | ☐ No | ☐ No
FOUND-001 | Foundation & Config | Database foundation | Initialize SQLite + Drizzle client and migrations | P0 | Not Started |  | 6 |  |  |  | Not Started | Database initializes and migrations are repeatable. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery source | Implement Agent Reach adapter for LinkedIn job discovery | P0 | Not Started |  | 8 |  |  |  | Not Started | Normalized raw listings can be fetched with retries/rate limits. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery pipeline | Normalize external listings into canonical job representation | P0 | Not Started | DISC-001 | 5 |  |  |  | Not Started | Equivalent source records map to one canonical shape. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery pipeline | Deduplicate against active queue and historical jobs/applications | P0 | Not Started | DISC-002 | 5 |  |  |  | Not Started | Previously processed jobs are not re-enqueued. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery safety | Add source rate limits, retry/backoff and failure persistence | P1 | Not Started | DISC-001 | 4 |  |  |  | Not Started | Failures do not lose queued jobs or crash the run. |  | ☐ No | ☐ No
MATCH-001 | Matching & Classification | Matching | Implement candidate/job fit scoring with configurable LLM provider | P0 | Not Started |  | 8 |  |  |  | Not Started | Returns score plus explicit gap analysis. |  | ☐ No | ☐ No
MATCH-001 | Matching & Classification | Classification | Classify jobs as application-eligible, stretch, or not-qualified | P0 | Not Started | MATCH-001 | 5 |  |  |  | Not Started | Classification is persisted and threshold is configurable. |  | ☐ No | ☐ No
MATCH-001 | Matching & Classification | Prioritization | Rank eligible jobs using fit and candidate preferences | P0 | Not Started | MATCH-001 | 4 |  |  |  | Not Started | Deterministic ordering for same inputs. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Persistence | Implement persistent opportunity queue | P0 | Not Started |  | 6 |  |  |  | Not Started | Unused qualifying jobs survive daily runs. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Queue lifecycle | Remove applied/rejected/completed items from active queue while retaining history | P0 | Not Started | QUEUE-001 | 4 |  |  |  | Not Started | Historical records remain queryable. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Stretch jobs | Persist/report stretch opportunities separately from application queue | P1 | Not Started | MATCH-002 | 4 |  |  |  | Not Started | Stretch jobs are visible in EOD reporting and are not auto-applied. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Daily target | Select at most remaining daily application capacity | P0 | Not Started | QUEUE-001,RUN-002 | 4 |  |  |  | Not Started | Never exceeds configured daily target. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Scheduler | Implement 10:00 default scheduled trigger with configurable time/timezone | P0 | Not Started | FOUND-002 | 5 |  |  |  | Not Started | Scheduler fires at configured local time. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Manual trigger | Implement Run Now using the exact same DailyRunOrchestrator | P0 | Not Started | RUN-001 | 5 |  |  |  | Not Started | Manual and scheduled runs share orchestration path. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Daily orchestrator | Inspect existing queue first and discover only if capacity cannot be met | P0 | Not Started | QUEUE-004,RUN-002 | 8 |  |  |  | Not Started | Queue-first behavior is observable and tested. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Daily orchestrator | Repeat discover → match → tailor → execute → save until target or no viable jobs | P0 | Not Started | RUN-003 | 8 |  |  |  | Not Started | Loop terminates safely and preserves leftovers. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Run tracking | Persist daily run state, counts, trigger type, start/end and outcome | P1 | Not Started | FOUND-004 | 5 |  |  |  | Not Started | Each run has complete audit metadata. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Tailoring | Create master candidate facts source of truth | P0 | Not Started | FOUND-004 | 5 |  |  |  | Not Started | Generated content can only use verified facts. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Tailoring | Generate per-job tailored CV content and application answers | P0 | Not Started | MATCH-003,CV-001 | 10 |  |  |  | Not Started | Tailoring is traceable to job and candidate facts. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Document versioning | Persist CV version metadata and exact Google Drive file ID | P0 | Not Started | CV-002 | 5 |  |  |  | Not Started | Application references exact submitted CV version. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Document generation | Generate PDF/DOCX and store in Google Drive | P0 | Not Started | CV-003 | 8 |  |  |  | Not Started | Generated file is retrievable from Drive. |  | ☐ No | ☐ No
VAL-001 | Validation | Factual validation | Validate CV/answers against verified candidate facts | P0 | Not Started | CV-002 | 6 |  |  |  | Not Started | Unsupported claims block execution. |  | ☐ No | ☐ No
VAL-001 | Validation | Application validation | Validate required fields, links and document references | P0 | Not Started | CV-004 | 5 |  |  |  | Not Started | Invalid application draft cannot reach executor. |  | ☐ No | ☐ No
APP-001 | Application Automation | Browser Use | Build isolated browser execution runner for Easy Apply/forms | P0 | Not Started | APPR-001,VAL-002 | 10 |  |  |  | Not Started | Runner executes only approved, validated actions. |  | ☐ No | ☐ No
APP-001 | Application Automation | Application lifecycle | Handle success, failure, unmapped input and retry/idempotency | P0 | Not Started | APP-001 | 8 |  |  |  | Not Started | Duplicate submissions are prevented. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Approval model | Create generic execution request/approval model shared by applications, DMs and posts | P0 | Not Started |  | 7 |  |  |  | Not Started | One approval abstraction supports all three action types. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Manual mode | Implement email approval with expiring single-use approve/reject actions where feasible | P0 | Not Started | APPR-001 | 8 |  |  |  | Not Started | Only authenticated/valid approval token can execute. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Dashboard fallback | Implement dashboard approval/rejection when email action is unavailable | P0 | Not Started | APPR-001 | 6 |  |  |  | Not Started | Same execution request is visible in UI. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Autonomous mode | Implement MANUAL/AUTONOMOUS toggles without allowing agent self-escalation | P0 | Not Started | APPR-001 | 5 |  |  |  | Not Started | Only trusted config can enable autonomous execution. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Recruiter discovery | Identify relevant recruiters for qualified jobs | P1 | Not Started | MATCH-003 | 6 |  |  |  | Not Started | Recruiter targets are linked to job/company. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Messaging | Generate personalized recruiter DMs and follow-ups | P1 | Not Started | OUT-001 | 6 |  |  |  | Not Started | Messages use verified candidate facts and job context. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Messaging | Queue approval requests and dispatch approved messages via Unipile | P0 | Not Started | APPR-001,OUT-002 | 6 |  |  |  | Not Started | No message is dispatched in MANUAL mode without approval. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Relationship tracking | Track replies and follow-up due state | P1 | Not Started | OUT-003 | 5 |  |  |  | Not Started | Inbound/reply state is auditable. |  | ☐ No | ☐ No
POST-001 | LinkedIn Content | Content | Generate professional LinkedIn post draft approximately every 2 days | P1 | Not Started | RUN-005 | 5 |  |  |  | Not Started | Draft is grounded in candidate activity/facts. |  | ☐ No | ☐ No
POST-001 | LinkedIn Content | Publication | Queue approval and publish/schedule after approval | P0 | Not Started | APPR-001,POST-001 | 6 |  |  |  | Not Started | No publication occurs without required approval in MANUAL mode. |  | ☐ No | ☐ No
DRIVE-001 | Google Drive | Storage | Implement scoped Google Drive integration | P0 | Not Started | FOUND-001 | 7 |  |  |  | Not Started | Access is limited to required document storage. |  | ☐ No | ☐ No
DRIVE-001 | Google Drive | Organization | Create deterministic folders/naming/version metadata for CVs | P1 | Not Started | DRIVE-001,CV-003 | 4 |  |  |  | Not Started | Every document maps to candidate/job/application. |  | ☐ No | ☐ No
RPT-001 | Reporting | EOD report | Compile applications, rejections, stretch jobs, outreach, failures and leftovers | P0 | Not Started | RUN-005 | 6 |  |  |  | Not Started | Report reflects persisted state. |  | ☐ No | ☐ No
RPT-001 | Reporting | Email | Send EOD report via configured email provider/SMTP | P0 | Not Started | RPT-001 | 4 |  |  |  | Not Started | Delivery failures are logged and retried safely. |  | ☐ No | ☐ No
DASH-001 | Dashboard | Control dashboard | Show queue, applications, drafts, approvals, settings and run status | P0 | Not Started | RUN-005,APPR-003 | 10 |  |  |  | Not Started | Candidate can inspect and control all manual actions. |  | ☐ No | ☐ No
DASH-001 | Dashboard | Manual trigger | Add Run Now control with confirmation and run status | P0 | Not Started | RUN-002 | 4 |  |  |  | Not Started | Invokes same orchestrator as scheduler. |  | ☐ No | ☐ No
SEC-001 | Security | Secrets | Secure env/secret handling; never log tokens/cookies/credentials | P0 | Not Started |  | 6 |  |  |  | Not Started | Secret scan passes; sensitive values never appear in logs. |  | ☐ No | ☐ No
SEC-001 | Security | Access control | Protect dashboard and approval endpoints; fail closed | P0 | Not Started | DASH-001 | 8 |  |  |  | Not Started | Unauthenticated/invalid requests cannot execute actions. |  | ☐ No | ☐ No
SEC-001 | Security | Agent permissions | Enforce allowlisted tools/files/actions and prevent self-escalation | P0 | Not Started | FOUND-001 | 8 |  |  |  | Not Started | Agent cannot change its own permissions or execution modes. |  | ☐ No | ☐ No
SEC-001 | Security | Browser isolation | Isolate browser sessions and restrict data/network access | P0 | Not Started | APP-001 | 7 |  |  |  | Not Started | Browser runner cannot access unrelated secrets/resources. |  | ☐ No | ☐ No
SEC-001 | Security | Input/LLM safety | Validate external inputs and treat LLM output as untrusted data | P0 | Not Started | MATCH-001,CV-002 | 7 |  |  |  | Not Started | Prompt injection cannot directly trigger privileged actions. |  | ☐ No | ☐ No
SEC-001 | Security | Audit/idempotency | Audit consequential actions and prevent duplicate execution | P0 | Not Started | APPR-001,APP-002 | 6 |  |  |  | Not Started | Every external action has traceable immutable-ish event history. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Unit tests | Test normalization, dedupe, matching classification and queue state transitions | P0 | Not Started | DISC-003,MATCH-002,QUEUE-002 | 8 |  |  |  | Not Started | Core domain tests pass. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Orchestrator tests | Test queue-first, daily target, manual trigger and scheduled trigger | P0 | Not Started | RUN-003 | 8 |  |  |  | Not Started | Manual/scheduled paths behave identically. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Approval tests | Test email approval, dashboard fallback, rejection and autonomous toggles | P0 | Not Started | APPR-002,APPR-003,APPR-004 | 8 |  |  |  | Not Started | No unauthorized execution occurs. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Security tests | Run dependency audit, secret scanning, auth/authorization and prompt-injection tests | P0 | Not Started | SEC-001,SEC-005 | 8 |  |  |  | Not Started | Security acceptance checklist passes. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | End-to-end | Run controlled sandbox E2E with Browser Use and mock/external integration boundaries | P0 | Not Started | TEST-001,TEST-002,TEST-003 | 12 |  |  |  | Not Started | End-to-end flow is repeatable without duplicate submissions. |  | ☐ No | ☐ No

## FOUND - Foundation & Config
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
FOUND-001 | Foundation & Config | Project configuration | Define runtime config schema and environment loading | P0 | Not Started |  | 4 |  |  |  | Not Started | Validated config loads with safe defaults. |  | ☐ No | ☐ No
FOUND-001 | Foundation & Config | Project configuration | Add daily run time/timezone/default 10:00 and daily application target | P0 | Not Started | FOUND-001 | 3 |  |  |  | Not Started | Defaults are 10:00 and configurable; invalid values fail closed. |  | ☐ No | ☐ No
FOUND-001 | Foundation & Config | Project configuration | Add independent application/DM/post execution mode variables, default MANUAL | P0 | Not Started | FOUND-001 | 3 |  |  |  | Not Started | Each mode accepts MANUAL/AUTONOMOUS and defaults to MANUAL. |  | ☐ No | ☐ No
FOUND-001 | Foundation & Config | Database foundation | Initialize SQLite + Drizzle client and migrations | P0 | Not Started |  | 6 |  |  |  | Not Started | Database initializes and migrations are repeatable. |  | ☐ No | ☐ No

## DISC - Discovery
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
DISC-001 | Discovery | Discovery source | Implement Agent Reach adapter for LinkedIn job discovery | P0 | Not Started |  | 8 |  |  |  | Not Started | Normalized raw listings can be fetched with retries/rate limits. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery pipeline | Normalize external listings into canonical job representation | P0 | Not Started | DISC-001 | 5 |  |  |  | Not Started | Equivalent source records map to one canonical shape. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery pipeline | Deduplicate against active queue and historical jobs/applications | P0 | Not Started | DISC-002 | 5 |  |  |  | Not Started | Previously processed jobs are not re-enqueued. |  | ☐ No | ☐ No
DISC-001 | Discovery | Discovery safety | Add source rate limits, retry/backoff and failure persistence | P1 | Not Started | DISC-001 | 4 |  |  |  | Not Started | Failures do not lose queued jobs or crash the run. |  | ☐ No | ☐ No

## MATCH - Matching & Classific
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
MATCH-001 | Matching & Classification | Matching | Implement candidate/job fit scoring with configurable LLM provider | P0 | Not Started |  | 8 |  |  |  | Not Started | Returns score plus explicit gap analysis. |  | ☐ No | ☐ No
MATCH-001 | Matching & Classification | Classification | Classify jobs as application-eligible, stretch, or not-qualified | P0 | Not Started | MATCH-001 | 5 |  |  |  | Not Started | Classification is persisted and threshold is configurable. |  | ☐ No | ☐ No
MATCH-001 | Matching & Classification | Prioritization | Rank eligible jobs using fit and candidate preferences | P0 | Not Started | MATCH-001 | 4 |  |  |  | Not Started | Deterministic ordering for same inputs. |  | ☐ No | ☐ No

## QUEUE - Opportunity Queue
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
QUEUE-001 | Opportunity Queue | Persistence | Implement persistent opportunity queue | P0 | Not Started |  | 6 |  |  |  | Not Started | Unused qualifying jobs survive daily runs. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Queue lifecycle | Remove applied/rejected/completed items from active queue while retaining history | P0 | Not Started | QUEUE-001 | 4 |  |  |  | Not Started | Historical records remain queryable. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Stretch jobs | Persist/report stretch opportunities separately from application queue | P1 | Not Started | MATCH-002 | 4 |  |  |  | Not Started | Stretch jobs are visible in EOD reporting and are not auto-applied. |  | ☐ No | ☐ No
QUEUE-001 | Opportunity Queue | Daily target | Select at most remaining daily application capacity | P0 | Not Started | QUEUE-001,RUN-002 | 4 |  |  |  | Not Started | Never exceeds configured daily target. |  | ☐ No | ☐ No

## RUN - Daily Run & Schedule
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
RUN-001 | Daily Run & Scheduler | Scheduler | Implement 10:00 default scheduled trigger with configurable time/timezone | P0 | Not Started | FOUND-002 | 5 |  |  |  | Not Started | Scheduler fires at configured local time. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Manual trigger | Implement Run Now using the exact same DailyRunOrchestrator | P0 | Not Started | RUN-001 | 5 |  |  |  | Not Started | Manual and scheduled runs share orchestration path. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Daily orchestrator | Inspect existing queue first and discover only if capacity cannot be met | P0 | Not Started | QUEUE-004,RUN-002 | 8 |  |  |  | Not Started | Queue-first behavior is observable and tested. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Daily orchestrator | Repeat discover → match → tailor → execute → save until target or no viable jobs | P0 | Not Started | RUN-003 | 8 |  |  |  | Not Started | Loop terminates safely and preserves leftovers. |  | ☐ No | ☐ No
RUN-001 | Daily Run & Scheduler | Run tracking | Persist daily run state, counts, trigger type, start/end and outcome | P1 | Not Started | FOUND-004 | 5 |  |  |  | Not Started | Each run has complete audit metadata. |  | ☐ No | ☐ No

## CV - CV & Application Gen
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
CV-001 | CV & Application Generation | Tailoring | Create master candidate facts source of truth | P0 | Not Started | FOUND-004 | 5 |  |  |  | Not Started | Generated content can only use verified facts. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Tailoring | Generate per-job tailored CV content and application answers | P0 | Not Started | MATCH-003,CV-001 | 10 |  |  |  | Not Started | Tailoring is traceable to job and candidate facts. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Document versioning | Persist CV version metadata and exact Google Drive file ID | P0 | Not Started | CV-002 | 5 |  |  |  | Not Started | Application references exact submitted CV version. |  | ☐ No | ☐ No
CV-001 | CV & Application Generation | Document generation | Generate PDF/DOCX and store in Google Drive | P0 | Not Started | CV-003 | 8 |  |  |  | Not Started | Generated file is retrievable from Drive. |  | ☐ No | ☐ No

## VAL - Validation
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
VAL-001 | Validation | Factual validation | Validate CV/answers against verified candidate facts | P0 | Not Started | CV-002 | 6 |  |  |  | Not Started | Unsupported claims block execution. |  | ☐ No | ☐ No
VAL-001 | Validation | Application validation | Validate required fields, links and document references | P0 | Not Started | CV-004 | 5 |  |  |  | Not Started | Invalid application draft cannot reach executor. |  | ☐ No | ☐ No

## APP - Application Automati
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
APP-001 | Application Automation | Browser Use | Build isolated browser execution runner for Easy Apply/forms | P0 | Not Started | APPR-001,VAL-002 | 10 |  |  |  | Not Started | Runner executes only approved, validated actions. |  | ☐ No | ☐ No
APP-001 | Application Automation | Application lifecycle | Handle success, failure, unmapped input and retry/idempotency | P0 | Not Started | APP-001 | 8 |  |  |  | Not Started | Duplicate submissions are prevented. |  | ☐ No | ☐ No

## APPR - Approval & Execution
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
APPR-001 | Approval & Execution Modes | Approval model | Create generic execution request/approval model shared by applications, DMs and posts | P0 | Not Started |  | 7 |  |  |  | Not Started | One approval abstraction supports all three action types. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Manual mode | Implement email approval with expiring single-use approve/reject actions where feasible | P0 | Not Started | APPR-001 | 8 |  |  |  | Not Started | Only authenticated/valid approval token can execute. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Dashboard fallback | Implement dashboard approval/rejection when email action is unavailable | P0 | Not Started | APPR-001 | 6 |  |  |  | Not Started | Same execution request is visible in UI. |  | ☐ No | ☐ No
APPR-001 | Approval & Execution Modes | Autonomous mode | Implement MANUAL/AUTONOMOUS toggles without allowing agent self-escalation | P0 | Not Started | APPR-001 | 5 |  |  |  | Not Started | Only trusted config can enable autonomous execution. |  | ☐ No | ☐ No

## OUT - Recruiter Outreach
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
OUT-001 | Recruiter Outreach | Recruiter discovery | Identify relevant recruiters for qualified jobs | P1 | Not Started | MATCH-003 | 6 |  |  |  | Not Started | Recruiter targets are linked to job/company. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Messaging | Generate personalized recruiter DMs and follow-ups | P1 | Not Started | OUT-001 | 6 |  |  |  | Not Started | Messages use verified candidate facts and job context. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Messaging | Queue approval requests and dispatch approved messages via Unipile | P0 | Not Started | APPR-001,OUT-002 | 6 |  |  |  | Not Started | No message is dispatched in MANUAL mode without approval. |  | ☐ No | ☐ No
OUT-001 | Recruiter Outreach | Relationship tracking | Track replies and follow-up due state | P1 | Not Started | OUT-003 | 5 |  |  |  | Not Started | Inbound/reply state is auditable. |  | ☐ No | ☐ No

## POST - LinkedIn Content
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
POST-001 | LinkedIn Content | Content | Generate professional LinkedIn post draft approximately every 2 days | P1 | Not Started | RUN-005 | 5 |  |  |  | Not Started | Draft is grounded in candidate activity/facts. |  | ☐ No | ☐ No
POST-001 | LinkedIn Content | Publication | Queue approval and publish/schedule after approval | P0 | Not Started | APPR-001,POST-001 | 6 |  |  |  | Not Started | No publication occurs without required approval in MANUAL mode. |  | ☐ No | ☐ No

## DRIVE - Google Drive
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
DRIVE-001 | Google Drive | Storage | Implement scoped Google Drive integration | P0 | Not Started | FOUND-001 | 7 |  |  |  | Not Started | Access is limited to required document storage. |  | ☐ No | ☐ No
DRIVE-001 | Google Drive | Organization | Create deterministic folders/naming/version metadata for CVs | P1 | Not Started | DRIVE-001,CV-003 | 4 |  |  |  | Not Started | Every document maps to candidate/job/application. |  | ☐ No | ☐ No

## RPT - Reporting
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
RPT-001 | Reporting | EOD report | Compile applications, rejections, stretch jobs, outreach, failures and leftovers | P0 | Not Started | RUN-005 | 6 |  |  |  | Not Started | Report reflects persisted state. |  | ☐ No | ☐ No
RPT-001 | Reporting | Email | Send EOD report via configured email provider/SMTP | P0 | Not Started | RPT-001 | 4 |  |  |  | Not Started | Delivery failures are logged and retried safely. |  | ☐ No | ☐ No

## DASH - Dashboard
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
DASH-001 | Dashboard | Control dashboard | Show queue, applications, drafts, approvals, settings and run status | P0 | Not Started | RUN-005,APPR-003 | 10 |  |  |  | Not Started | Candidate can inspect and control all manual actions. |  | ☐ No | ☐ No
DASH-001 | Dashboard | Manual trigger | Add Run Now control with confirmation and run status | P0 | Not Started | RUN-002 | 4 |  |  |  | Not Started | Invokes same orchestrator as scheduler. |  | ☐ No | ☐ No

## SEC - Security
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
SEC-001 | Security | Secrets | Secure env/secret handling; never log tokens/cookies/credentials | P0 | Not Started |  | 6 |  |  |  | Not Started | Secret scan passes; sensitive values never appear in logs. |  | ☐ No | ☐ No
SEC-001 | Security | Access control | Protect dashboard and approval endpoints; fail closed | P0 | Not Started | DASH-001 | 8 |  |  |  | Not Started | Unauthenticated/invalid requests cannot execute actions. |  | ☐ No | ☐ No
SEC-001 | Security | Agent permissions | Enforce allowlisted tools/files/actions and prevent self-escalation | P0 | Not Started | FOUND-001 | 8 |  |  |  | Not Started | Agent cannot change its own permissions or execution modes. |  | ☐ No | ☐ No
SEC-001 | Security | Browser isolation | Isolate browser sessions and restrict data/network access | P0 | Not Started | APP-001 | 7 |  |  |  | Not Started | Browser runner cannot access unrelated secrets/resources. |  | ☐ No | ☐ No
SEC-001 | Security | Input/LLM safety | Validate external inputs and treat LLM output as untrusted data | P0 | Not Started | MATCH-001,CV-002 | 7 |  |  |  | Not Started | Prompt injection cannot directly trigger privileged actions. |  | ☐ No | ☐ No
SEC-001 | Security | Audit/idempotency | Audit consequential actions and prevent duplicate execution | P0 | Not Started | APPR-001,APP-002 | 6 |  |  |  | Not Started | Every external action has traceable immutable-ish event history. |  | ☐ No | ☐ No

## TEST - Testing & QA
ID | Module | Task | Sub-task | Priority | Status | Depends On | Estimated Hours | Start Date | End Date | PR No. | Test Status | Acceptance Criteria | Review Notes | Blocked? | Security Review? | Notes
TEST-001 | Testing & QA | Unit tests | Test normalization, dedupe, matching classification and queue state transitions | P0 | Not Started | DISC-003,MATCH-002,QUEUE-002 | 8 |  |  |  | Not Started | Core domain tests pass. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Orchestrator tests | Test queue-first, daily target, manual trigger and scheduled trigger | P0 | Not Started | RUN-003 | 8 |  |  |  | Not Started | Manual/scheduled paths behave identically. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Approval tests | Test email approval, dashboard fallback, rejection and autonomous toggles | P0 | Not Started | APPR-002,APPR-003,APPR-004 | 8 |  |  |  | Not Started | No unauthorized execution occurs. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | Security tests | Run dependency audit, secret scanning, auth/authorization and prompt-injection tests | P0 | Not Started | SEC-001,SEC-005 | 8 |  |  |  | Not Started | Security acceptance checklist passes. |  | ☐ No | ☐ No
TEST-001 | Testing & QA | End-to-end | Run controlled sandbox E2E with Browser Use and mock/external integration boundaries | P0 | Not Started | TEST-001,TEST-002,TEST-003 | 12 |  |  |  | Not Started | End-to-end flow is repeatable without duplicate submissions. |  | ☐ No | ☐ No